## Timeline
Complete | Event | Start/Event Date | End Date | Type | Label | Collection Team | Key?
TRUE | Spring Semester Begins | 2025-01-21 |  | Administrative | Academic Calendar |  | FALSE | Collection Teams:
TRUE | Capstone Kickoff | 2025-01-22 |  | Class | Capstone 1 |  | TRUE
TRUE | Proposal Draft #1 Due | 2025-01-29 |  | Assignment | Capstone 1 |  | FALSE | A - Parades, Marching Exhibitions | B - Large Pop/Rock Festivals (Rock Band), Medium Ceremonies, Formal Concerts | C - Large Pop/Rock Festivals (NOLA Brass Band) | D - Small Concerts, School Outreach, Small Ceremonies
TRUE | Capstone Advisor Meeting (Feb) | 2025-02-21 |  | Meeting | Capstone 1 |  | FALSE
TRUE | Research Plan Due | 2025-02-26 |  | Assignment | Capstone 1 |  | FALSE
TRUE | Capstone Group Meet | 2025-02-28 |  | Class | Capstone 1 |  | FALSE | KATUSA | KATUSA | KATUSA | KATUSA
FALSE | Survey Draft #1 | 2025-03-03 |  | Assignment | Quant II |  | FALSE | KATUSA | KATUSA | KATUSA | US
FALSE | Proposal Draft #2 Goal | 2025-03-14 |  | Assignment | Capstone 1 |  | FALSE | KATUSA | US | US
FALSE | Discussion Board #1 | 2025-03-15 |  | Assignment | Quant II |  | FALSE | KATUSA | US | US
FALSE | Presentation Slides Due | 2025-03-15 |  | Assignment | Capstone 1 |  | FALSE | US
FALSE | Capstone Advisor Meeting (Mar) | 2025-03-15 |  | Meeting | Capstone 1 |  | FALSE | US
FALSE | POP Presentation | 2025-03-20 |  | Assignment | Capstone 1 |  | FALSE | US
FALSE | Capstone Group Meet | 2025-03-21 |  | Class | Capstone 1 |  | FALSE | Total Engagements: | 32
FALSE | POP Proposal (Methods) Draft #1 | 2025-03-24 |  | Assignment | Quant II |  | FALSE
FALSE | DODEA Spring Break | 2025-03-28 | 2025-04-04 | Personal | Family |  | FALSE
FALSE | Survey Instrument Pilot Testing (Jinhae Cherry Blossom Festival) | 2025-04-01 | 2025-04-07 | Data Collection | Capstone 1 | A | TRUE
FALSE | Apply for Proposal Defense | 2025-04-01 |  | Administrative | Deadline |  | TRUE
FALSE | Discussion Board #2 | 2025-04-12 |  | Assignment | Quant II |  | FALSE
FALSE | POP Proposal (Methods) Draft #2 | 2025-04-14 |  | Assignment | Quant II |  | FALSE
FALSE | Proposal Draft #3 Goal | 2025-04-15 |  | Assignment | Capstone 1 |  | FALSE
FALSE | Capstone Advisor Meeting (Apr) | 2025-04-15 |  | Meeting | Capstone 1 |  | FALSE
FALSE | April Discussion Board | 2025-04-16 |  | Assignment | Capstone 1 |  | FALSE
FALSE | Capstone Group Meet | 2025-04-18 |  | Class | Capstone 1 |  | FALSE
FALSE | Survey Final | 2025-04-28 |  | Assignment | Quant II |  | FALSE
FALSE | May Discussion Board | 2025-04-30 |  | Assignment | Capstone 1 |  | FALSE
FALSE | POP Proposal (Methods) Final | 2025-05-06 |  | Assignment | Quant II |  | FALSE
FALSE | Spring Semester Ends | 2025-05-06 |  | Administrative | Academic Calendar |  | FALSE
FALSE | Proposal Defense Document Submission | 2025-05-14 |  | Goal | Capstone 2 |  | TRUE
FALSE | Capstone Advisor Meeting (May) | 2025-05-15 |  | Meeting | Capstone 1 |  | FALSE
FALSE | Discussion Board #3 | 2025-05-17 |  | Assignment | Quant II |  | FALSE
FALSE | Group Presentation Slides Due | 2025-05-17 |  | Assignment | Capstone 1 |  | FALSE
FALSE | Summer Term Begins | 2025-05-19 |  | Administrative | Academic Calendar |  | FALSE
FALSE | Capstone Group Meet | 2025-05-23 |  | Class | Capstone 1 |  | FALSE
FALSE | Group Presentation | 2025-05-23 |  | Assignment | Capstone 1 |  | FALSE
FALSE | Proposal Defense | 2025-06-01 |  | Goal | Capstone 2 |  | TRUE
FALSE | ROKA GOC Joint Concert | 2025-06-01 |  | Data Collection | Engagement | A | FALSE
FALSE | Data Collection | 2025-06-02 | 2025-12-15 | Data Collection | Capstone 2 |  | TRUE
FALSE | ROKA TRADOC Joint Concert | 2025-06-02 |  | Data Collection | Engagement | A | FALSE
FALSE | DODEA School Ends | 2025-06-10 |  | Personal | Family |  | FALSE
FALSE | Summer Vacation | 2025-06-12 | 2025-06-29 | Personal | Family |  | FALSE
FALSE | K-16 Summer Music Festival | 2025-06-14 |  | Data Collection | Engagement | B | FALSE
FALSE | Capstone Advisor Meeting (Jun) | 2025-06-15 |  | Meeting | Capstone 2 |  | FALSE
FALSE | Deagu Liberty Fest | 2025-06-28 |  | Data Collection | Engagement | B | FALSE
FALSE | Doosan Bears Baseball Event | 2025-06-28 |  | Data Collection | Engagement | A | FALSE
FALSE | Data Analysis | 2025-07-01 | 2025-12-15 | Analysis | Capstone 3 |  | FALSE
FALSE | Pocheon US Independence Day Concert | 2025-07-01 |  | Data Collection | Engagement | A | TRUE
FALSE | Apply to Graduate (window) | 2025-07-01 | 2025-10-15 | Administrative | Deadline |  | TRUE
FALSE | Battle of Daejon Ceremony | 2025-07-11 |  | Data Collection | Engagement | D | FALSE
FALSE | Capstone Advisor Meeting (Jul) | 2025-07-15 |  | Meeting | Capstone 2 |  | FALSE
FALSE | Korean War Armistice Agreement Ceremony | 2025-07-27 |  | Data Collection | Engagement | B | FALSE
FALSE | Suwon I'm Soldier Show | 2025-07-31 |  | Data Collection | Engagement | C | FALSE
FALSE | Jeju Island Wind Ensemble Festival | 2025-08-07 | 2025-08-11 | Data Collection | Engagement | A | TRUE
FALSE | Write Up Data and Findings | 2025-08-08 | 2025-12-15 | Writing | Capstone 2 |  | FALSE
FALSE | Daejeon One o'clock Festival | 2025-08-08 | 2025-08-16 | Data Collection | Engagement | B | TRUE
FALSE | Milal School | 2025-08-13 |  | Data Collection | Engagement | D | FALSE
FALSE | Summer Term Ends | 2025-08-13 |  | Administrative | Academic Calendar |  | FALSE
FALSE | Capstone Advisor Meeting (Aug) | 2025-08-15 |  | Meeting | Capstone 2 |  | FALSE
FALSE | DODEA School Begins | 2025-08-18 |  | Personal | Family |  | FALSE
FALSE | Dongducheon Music Festival | 2025-09-01 |  | Data Collection | Engagement | B | FALSE
FALSE | Fall Semester Begins | 2025-09-02 |  | Administrative | Academic Calendar |  | FALSE
FALSE | ROKN 80th Anniversary Joint Concert Tour | 2025-09-05 | 2025-09-11 | Data Collection | Engagement | A | FALSE
FALSE | Humphreys Ham Jam | 2025-09-07 |  | Data Collection | Engagement | B | FALSE
FALSE | Jumong School | 2025-09-12 |  | Data Collection | Engagement | D | FALSE
FALSE | Landers Baseball Event | 2025-09-15 |  | Data Collection | Engagement | A | FALSE
FALSE | Capstone Advisor Meeting (Sep) | 2025-09-15 |  | Meeting | Capstone 2 |  | FALSE
FALSE | Humphreys Fall Fest & One Heart Festival | 2025-09-27 |  | Data Collection | Engagement | B | FALSE
FALSE | Gimpo World Culture Festival | 2025-09-29 |  | Data Collection | Engagement | B | FALSE
FALSE | Gyeryang Ground Forces Festival | 2025-10-01 | 2025-10-07 | Data Collection | Engagement | A | TRUE
FALSE | ROK Armed Forces Day Parade | 2025-10-01 |  | Data Collection | Engagement | A | TRUE
FALSE | Battle of Nakdong Victory Ceremony | 2025-10-04 | 2025-09-05 | Data Collection | Engagement | B | TRUE
FALSE | Capstone Advisor Meeting (Oct) | 2025-10-15 |  | Meeting | Capstone 3 |  | FALSE
FALSE | Gyonam School | 2025-10-25 |  | Data Collection | Engagement | D | FALSE
FALSE | Apply for POP Defense | 2025-11-01 |  | Administrative | Deadline |  | TRUE
FALSE | PIEF Concert | 2025-11-12 |  | Data Collection | Engagement | B | FALSE
FALSE | Woojin School | 2025-11-15 |  | Data Collection | Engagement | D | FALSE
FALSE | Capstone Advisor Meeting (Nov) | 2025-11-15 |  | Meeting | Capstone 3 |  | FALSE
FALSE | Osan Jazz Festival | 2025-11-18 |  | Data Collection | Engagement | C | FALSE
FALSE | Osan Santa Market | 2025-11-23 |  | Data Collection | Engagement | C | FALSE
FALSE | Gwangjin School | 2025-12-10 |  | Data Collection | Engagement | D | FALSE
FALSE | PIEF Winter Concert | 2025-12-11 |  | Data Collection | Engagement | C | FALSE
FALSE | Pocheon OP: Santa Claus | 2025-12-12 |  | Data Collection | Engagement | D | FALSE
FALSE | Taewon School | 2025-12-13 |  | Data Collection | Engagement | D | FALSE
FALSE | Dongucheon Year-End Concert | 2025-12-14 |  | Data Collection | Engagement | B | FALSE
FALSE | Final POP Writeup | 2025-12-15 | 2026-01-01 | Writing | Capstone 3 |  | FALSE
FALSE | Capstone Advisor Meeting (Dec) | 2025-12-15 |  | Meeting | Capstone 3 |  | FALSE
FALSE | Fall Semester Ends | 2025-12-21 |  | Administrative | Academic Calendar |  | FALSE
FALSE | Winter Vacation | 2025-12-21 | 2026-01-04 | Personal | Family |  | FALSE
FALSE | DODEA Winter Break | 2025-12-22 | 2026-01-02 | Personal | Family |  | FALSE
FALSE | Final POP Defense Submission | 2026-01-02 |  | Goal | Capstone 3 |  | TRUE
FALSE | January Term Begins | 2026-01-05 |  | Administrative | Academic Calendar |  | FALSE
FALSE | Capstone Advisor Meeting (Jan) | 2026-01-15 |  | Meeting | Capstone 4 |  | FALSE
FALSE | January Term Ends | 2026-01-16 |  | Administrative | Academic Calendar |  | FALSE
FALSE | Final POP Defense | 2026-01-31 |  | Goal | Capstone 3 |  | TRUE
FALSE | Defended POP Due | 2026-02-21 |  | Goal | Capstone 4 |  | TRUE
FALSE | DODEA Spring Break | 2026-03-27 | 2026-04-03 | Personal | Family |  | FALSE
FALSE | Graduation (Doctoral Convocation) | 2026-05-09 |  | Goal | Capstone 4 |  | TRUE
FALSE | DODEA Accelerated Withdrawl | 2026-05-12 |  | Personal | Family |  | FALSE
FALSE | Change of Command | 2026-06-06 |  | Personal | Professional |  | FALSE
FALSE | DODEA School Ends | 2026-06-09 |  | Personal | Family |  | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE
FALSE | [6 empty] | FALSE

## Engagment Details
Event ID | Event | Start Date | End Data | Survey Team | Performance Type | Event Confirmed? | Survey Team Assigned? | Survey Reviewed? | QR Code Produced? | Survey Incentives? | Est. Audience Count | Survey Responses
PILOT-1 | Survey Instrument Pilot Testing (Jinhae Cherry Blossom Festival) | 2025-04-01 | 2025-04-07 | A | Multiple (Festival) | FALSE | FALSE | FALSE | FALSE
CJ-01 | ROKA GOC Joint Concert | 2025-06-01 |  | A | Concert (Joint) | FALSE | FALSE | FALSE | FALSE
CJ-02 | ROKA TRADOC Joint Concert | 2025-06-02 |  | A | Concert (Joint) | FALSE | FALSE | FALSE | FALSE
MF-01 | K-16 Summer Music Festival | 2025-06-14 |  | B | Music Festival | FALSE | FALSE | FALSE | FALSE
UF-01 | Deagu Liberty Fest | 2025-06-28 |  | B | Festival (US) | FALSE | FALSE | FALSE | FALSE
PC-01 | Doosan Bears Baseball Event | 2025-06-28 |  | A | Parade/Ceremony | FALSE | FALSE | FALSE | FALSE
CJ-03 | Pocheon US Independence Day Concert | 2025-07-01 |  | A | Concert (Joint) | FALSE | FALSE | FALSE | FALSE
PC-02 | Battle of Daejon Ceremony | 2025-07-11 |  | D | Parade/Ceremony | FALSE | FALSE | FALSE | FALSE
PC-03 | Korean War Armistice Agreement Ceremony | 2025-07-27 |  | B | Parade/Ceremony | FALSE | FALSE | FALSE | FALSE
CS-01 | Suwon I'm Soldier Show | 2025-07-31 |  | C | Concert Showcase | FALSE | FALSE | FALSE | FALSE
CU-01 | Jeju Island Wind Ensemble Festival | 2025-08-07 | 2025-08-11 | A | Concert (US) | FALSE | FALSE | FALSE | FALSE
MF-02 | Daejeon One o'clock Festival | 2025-08-08 | 2025-08-16 | B | Music Festival | FALSE | FALSE | FALSE | FALSE
SO-01 | Milal School | 2025-08-13 |  | D | School Outreach | FALSE | FALSE | FALSE | FALSE
MF-03 | Dongducheon Music Festival | 2025-09-01 |  | B | Music Festival | FALSE | FALSE | FALSE | FALSE
CJ-04 | ROKN 80th Anniversary Joint Concert Tour | 2025-09-05 | 2025-09-11 | A | Concert (Joint) | FALSE | FALSE | FALSE | FALSE
UF-02 | Humphreys Ham Jam | 2025-09-07 |  | B | Festival (US) | FALSE | FALSE | FALSE | FALSE
SO-02 | Jumong School | 2025-09-12 |  | D | School Outreach | FALSE | FALSE | FALSE | FALSE
PC-04 | Landers Baseball Event | 2025-09-15 |  | A | Parade/Ceremony | FALSE | FALSE | FALSE | FALSE
UF-03 | Humphreys Fall Fest & One Heart Festival | 2025-09-27 |  | B | Festival (US) | FALSE | FALSE | FALSE | FALSE
RF-01 | Gimpo World Culture Festival | 2025-09-29 |  | B | Cultural Festival (ROK) | FALSE | FALSE | FALSE | FALSE
RF-02 | Gyeryang Ground Forces Festival | 2025-10-01 | 2025-10-07 | A | Multiple (Marching & Festival) | FALSE | FALSE | FALSE | FALSE
PC-05 | ROK Armed Forces Day Parade | 2025-10-01 |  | A | Parade/Ceremony | FALSE | FALSE | FALSE | FALSE
RF-03 | Battle of Nakdong Victory Ceremony | 2025-10-04 | 2025-09-05 | B | Multiple (Festival & Ceremony) | FALSE | FALSE | FALSE | FALSE
SO-03 | Gyonam School | 2025-10-25 |  | D | School Outreach | FALSE | FALSE | FALSE | FALSE
CS-02 | PIEF Concert | 2025-11-12 |  | B | Concert Showcase | FALSE | FALSE | FALSE | FALSE
SO-04 | Woojin School | 2025-11-15 |  | D | School Outreach | FALSE | FALSE | FALSE | FALSE
MF-04 | Osan Jazz Festival | 2025-11-18 |  | C | Music Festival | FALSE | FALSE | FALSE | FALSE
PC-06 | Osan Santa Market | 2025-11-23 |  | C | Parade/Ceremony | FALSE | FALSE | FALSE | FALSE
SO-05 | Gwangjin School | 2025-12-10 |  | D | School Outreach | FALSE | FALSE | FALSE | FALSE
CS-03 | PIEF Winter Concert | 2025-12-11 |  | C | Concert Showcase | FALSE | FALSE | FALSE | FALSE
SO-06 | Pocheon OP: Santa Claus | 2025-12-12 |  | D | School Outreach | FALSE | FALSE | FALSE | FALSE
SO-07 | Taewon School | 2025-12-13 |  | D | School Outreach | FALSE | FALSE | FALSE | FALSE
CS-04 | Dongucheon Year-End Concert | 2025-12-14 |  | B | Concert Showcase | FALSE | FALSE | FALSE | FALSE
Engagement Types:
| Parades & Ceremonies (PC) | 6
| Joint Concert (CJ) | 4
| Concert US-only (CU) | 1
| Concert Showcase (CS) | 4
| School Outreach (SO) | 7
| Music Festival (MF) | 4
| US-hosted Cultural Festival (UF) | 3
| ROK-hosted Cultural Festival (RF) | 3
Total Est. Audience:
Total Survey Respones